X:\CareerDevMonth\2013\NCDMitems.docx

(FEBRUARY-August)

Nominations (CIS will send these to Vicki and to Jennifer on the ICDA Board)

- Start advertising and soliciting in nominations in February.  Due date September 1st.

  - Post on sites

    - CIS

    - ICDA

  - Nominations:

    - Nominations from Field

    - CIS nominations (CIS need to finished- Christian to do)

    - ICDA nominations?

ICDA Budget for Events and Awards

- Determine budget

  - Plaques

  - Social

(MAY)

Contact Governor’s Office

- Contact the governor’s office to request the proclamation in May

  - Fill out appropriate form

  - Request the signing ceremony at the same time

  - Follow up six weeks prior to the event to see if we have a ceremony approved.

(SEPTEMBER)

Choose winners

Write up small blurb/speech for each nominee

- Look at last year’s and create something similar

- Make sure that CIS and ICDA have a copy

Notify Winners

- Wait to notify until we know when signing ceremony/ ICDA social will be

  - No later than the end of September, beginning of October to give them a month for planning

Invite DOL Staff and Management

- Let DOL staff know this is a joint effort this year by DOL/ ICDA

- Send invite to Roger, Georgia, and Area Managers first

- Send invite to “Everyone” group in Outlook

  - As soon as we know the date we need to contact Cheryl Ausman to put on Roger’s calendar

  - Express that if Roger would like to talk he is more than welcome to do so.

    - If he would like to make sure he gets a copy of the speech so he can refer to that.

  - Need to get on Georgia’s calendar as well

- Follow up email to go the week before

Outreach Materials (Post November 1st)

- Press Release- CIS and ICDA

- CIS Portal- CIS

- ICDA Site- Amy Brady

Governor Office Signing Ceremony

- Communicate with Bobbi Jo Meulman to determine if this is will happen

  - Ask if it is okay to give awards away during the signing ceremony

  - Bobbi-Jo.Meuleman@gov.idaho.gov

(OCTOBER)

Outreach Materials

- Communicate to partners date/time/locations

- Ask for RSVP

Awards/Plaques

- ICDA will order/ create the awards/ plaques

- ICDA will ship to any winner not available to attend the day’s events

Proclamation

- Post online by October 31st

  - CIS

  - ICDA

Singing Ceremony

- Invite Partners

  - Keep a list of RSVPs:

    - Need to provide this to the Gov Staff in advance

    - Example from last year attached

  - If we have the OK to give awards away send the write up on each person to the Gov staff.

Career Development Social

- Invite partners

- Set up location and time

- Determine what food /drinks will be offered

November (day of)

- Reminder to partners

- Set up location

- Good Job everyone, Enjoy!